## Worksheet
Project Name | Team Member | Start Date | End Date | Status | Progress (%) | Key Deliverables | Issues / Risks | Next Action Steps
Web Platform Redesign | Alex Morgan | 2024-01-15 | 2024-06-30 | On Track | 75% | Homepage redesign, Mobile responsive layout, UX audit | Delayed third-party API integration (estimated 2 weeks) | Complete API integration by May 10; finalize UI mockups
Customer Support Automation | Samira Patel | 2024-02-01 | 2024-08-15 | On Track | 60% | Chatbot deployment, Ticket routing system, Knowledge base update | Need additional training for support staff | Schedule training session on May 15; finalize bot testing plan
Mobile App Enhancement | Jordan Lee | 2024-03-10 | 2024-10-31 | At Risk | 45% | Performance optimization, Push notification feature, Dark mode | Critical bug in payment flow; server bandwidth issues | Fix payment bug by April 20; review server capacity plan
Marketing Campaign Launch | Taylor Reed | 2024-04-05 | 2024-05-31 | Completed | 100% | Social media blitz, Email sequence, SEO content rollout | None reported | Results analysis to be submitted by June 5