## Worksheet
Project Name | Team Member | Start Date | End Date | Current Status | Progress (%) | Key Milestones | Next Actions | Owner Responsibility
Product Launch Q3 | Sarah Johnson | 2024-07-01 | 2024-09-30 | On Track | 85% | UI Design Finalized, Beta Testing Started | Complete final testing by 09/15 | Sarah Johnson
Customer Analytics Upgrade | Mike Chen | 2024-08-15 | 2024-10-31 | In Progress | 45% | Data Integration, Dashboard Prototype | Finalize data model by 09/01 | Mike Chen
Mobile App Redesign | Lisa Wong | 2024-06-10 | 2024-11-30 | Planning Phase | 15% | User Research Completed, Wireframes Drafted | Begin usability testing by 08/20 | Lisa Wong
Marketing Campaign Rollout | David Kim | 2024-09-01 | 2024-10-31 | Pending Approval | 5% | Content Finalized, Budget Approved | Wait for executive sign-off by 09/10 | David Kim