## Worksheet
Project Name | Objective | Start Date | End Date | Current Status | Progress (%) | Responsible Team | Key Milestones | Risk Level | Next Review Date
Product Launch 2024 | Launch new mobile application with enhanced user interface. | 2024-01-15 | 2024-06-30 | In Progress | 65% | Product & UX Team | Milestone 1: Design Approved (Completed) Milestone 2: Beta Testing (Pending) | Medium | 2024-05-15
Customer Onboarding Platform | Improve customer onboarding flow and reduce drop-off rate. | 2024-02-01 | 2024-08-31 | Pending Start | - | Customer Success & DevOps Team | Milestone 1: Requirement Finalized (Pending)Milestone 2: MVP Build (Scheduled) | Low | 2024-03-15
AI Integration Project | Integrate AI chatbot into support portal for faster resolution. | 2024-03-10 | 2024-12-31 | On Hold | - | Engineering & AI Team | Milestone 1: Data Collection (Completed) Milestone 2: Model Training (On Hold) | High | 2024-04-10
Global Expansion Initiative | Enter European market with localized content and legal compliance. | 2024-04-05 | 2025-12-31 | Planning Phase | - | Marketing & Legal Team