## Worksheet
Date | Project Name | Task | Progress (%) | Status | Owner | Notes
2023-10-03 | Website Redesign | UI/UX Design Finalization | 85% | On Track | Sarah Chen | Client feedback incorporated; mockups approved.
2023-10-03 | Mobile App Development | Backend API Integration | 60% | On Track | James Reed | Testing with staging server in progress.
2023-10-03 | Marketing Campaign | Content Creation for Social Media | 95% | On Track | Lena Torres | All visuals and copy finalized and ready for posting.
2023-10-03 | Customer Onboarding System | User Flow Documentation | 45% | Delayed | Michael Kim | Waiting for final stakeholder review.