## Worksheet
Project Name | Start Date | End Date | Current Phase | Status | Key Milestones | Performance KPIs | Responsible Team | Progress (%) | Risk Level | Next Review Date
Digital Transformation Initiative | 2024-03-15 | 2025-09-30 | Phase 3 - Integration | On Track | System migration complete, API testing passed | Uptime > 99.9%, User adoption rate ≥ 85% | IT & Operations | 82% | Low | 2024-07-15
Customer Experience Platform Launch | 2024-04-01 | 2024-11-30 | Phase 2 - Beta Testing | On Track | Beta version released, user feedback collected | NPS ≥ 70, Response time ≤ 2s | Product & UX Team | 68% | Medium | 2024-08-10
Supply Chain Optimization Project | 2024-05-10 | 2025-03-15 | Phase 1 - Assessment | Delayed (Minor) | Vendor audit completed, process mapping done | Cost reduction target: 15%, Lead time down by 20% | Operations & Logistics | 45% | High | 2024-06-30