## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Progress (%) | Milestone?
Project Initiation | 2024-01-15 | 2024-01-31 | Project Manager | Completed | 100% | Yes
Requirements Gathering | 2024-02-01 | 2024-02-15 | Business Analysts | In Progress | 75% | No
Design Phase | 2024-02-16 | 2024-03-15 | UI/UX Team | Not Started | 0% | Yes
Development | 2024-03-16 | 2024-05-31 | Software Developers | Not Started | 0% | No
Testing & Quality Assurance | 2024-06-01 | 2024-07-15 | QA Team | Not Started | 0% | Yes
Deployment & Launch | 2024-07-16 | 2024-07-31 | IT Operations | Not Started | 0% | Yes
Post-Launch Review | 2024-08-01 | 2024-08-15 | Project Manager & Stakeholders | Not Started | 0% | Yes