## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Progress (%) | Key Milestone
Project Initiation & Planning | Jane Doe | 2024-03-01 | 2024-03-15 | On Track | 95% | Finalize project scope and budget
Market Research & Analysis | John Smith | 2024-03-16 | 2024-04-10 | In Progress | 65% | Complete competitive analysis report
Product Design & Prototyping | Lisa Chen | 2024-04-11 | 2024-05-30 | Not Started | 0% | Finalize product wireframes and prototypes
Development & Testing | Mike Rodriguez | 2024-06-01 | 2024-08-15 | Planned | 0% | Complete QA and performance testing
Launch Preparation & Marketing | Sarah Kim | 2024-08-16 | 2024-09-30 | Not Started | 0% | Execute launch campaign and training