## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Risk Level | Milestones | Notes
Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | Completed | 100% | None | Low | Meeting Scheduled
Requirements Gathering | John Smith | 2024-04-02 | 2024-04-15 | In Progress | 65% | Kickoff Meeting | Medium | Final Review Due 04/15 | Stakeholder feedback pending.
Design Phase Finalization | Alice Brown | 2024-04-16 | 2024-05-05 | Planned | 0% | Requirements Finalized | Low | Design Approval 05/03 | Prototype review scheduled.
Development Sprint 1 | Team A | 2024-05-06 | 2024-05-18 | Not Started | 0% | Design Finalized | Medium |  | Weekly stand-ups required.
User Testing & Feedback Loop | Sarah Lee | 2024-05-19 | 2024-06-10 | Planned | 0% | Development Sprint 1 Complete | High | Beta Launch 06/05 | Include accessibility review.
Final Deployment & Go-Live | IT Director | 2024-06-11 | 2024-06-15 | Not Started | 0% | Testing Complete | Low | Go-Live Confirmed 06/15 | Post-launch support begins.