## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Progress (%) | Notes
Project Initiation | 2024-01-15 | 2024-01-25 | Project Manager | Completed | 100%
Requirements Gathering | 2024-01-26 | 2024-02-15 | Business Analysts | In Progress | 75% | Finalizing user stories and acceptance criteria.
Design Phase | 2024-02-16 | 2024-03-10 | UI/UX Team | Not Started | 0%
Development Phase | 2024-03-11 | 2024-05-30 | Engineering Team | Not Started | 0%
Testing & Quality Assurance | 2024-06-01 | 2024-07-15 | QA Team | Not Started | 0%
Deployment & Go-Live | 2024-07-16 | 2024-07-31 | Operations Team | Not Started | 0%
Post-Deployment Review | 2024-08-01 | 2024-08-15 | Project Manager & Stakeholders | Not Started | 0%