## Worksheet
Task | Start Date | End Date | Status | Assigned To | Progress (%) | Priority
Project Planning & Scope Definition | 2024-03-01 | 2024-03-15 | Completed | Alex Rivera | 100% | High
Requirement Gathering & Analysis | 2024-03-16 | 2024-04-05 | In Progress | Jamie Lee | 75% | Medium
Design Phase - UI/UX Mockups | 2024-04-06 | 2024-04-25 | Not Started | Taylor Chen | 0% | High
Development - Backend Implementation | 2024-05-01 | 2024-06-15 | Not Started | Miguel Ortiz | 0% | High
Development - Frontend Implementation | 2024-06-16 | 2024-07-30 | Not Started | Sofia Kim | 0% | Medium
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | Not Started | Jordan Reed | 0% | High
User Training & Documentation | 2024-09-01 | 2024-09-15 | Not Started | Lena Patel | 0% | Medium
Go-Live & Post-Implementation Support | 2024-09-16 | 2024-10-31 | Not Started | Team Lead | 0% | Medium