## Worksheet
Month | Project Phase | Key Milestone | Target Date | Progress (%) | Responsible Team | Status
January | Planning & Requirements Gathering | Finalize project scope and stakeholder needs | 2024-01-31 | 85% | Product Team | On Track
February | Design & Wireframing | Complete UI/UX prototypes for all screens | 2024-02-28 | 60% | Design Team | On Track (Delayed by 3 days)
March | Development (Phase 1) | Launch backend API and core modules | 2024-03-31 | 40% | Engineering Team | At Risk
April | Development (Phase 2) | Integrate frontend with backend services | 2024-04-30 | 25% | Engineering Team | Delayed (Review pending)
May | Testing & Quality Assurance | Complete UAT and bug resolution | 2024-05-31 | 0% | QA Team | <Not Started
June | Deployment & Go-Live | Official launch to production environment | 2024-06-30 | 0% | Operations Team | Planned