## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%) | Dependencies
Project Initiation | 2024-01-01 | 2024-01-15 | Jane Doe | Completed | 100%
Requirements Gathering | 2024-01-16 | 2024-02-15 | John Smith | In Progress | 75% | Project Initiation
Design Phase | 2024-02-16 | 2024-03-31 | Alice Brown | Not Started | 0% | Requirements Gathering
Development | 2024-04-01 | 2024-06-30 | Mike Wilson | Not Started | 0% | Design Phase
Testing & QA | 2024-07-01 | 2024-08-15 | Sarah Lee | Not Started | 0% | Development
Deployment | 2024-08-16 | 2024-08-31 | David Chen | Not Started | 0% | Testing & QA
Post-Deployment Review | 2024-09-01 | 2024-09-15 | Jane Doe | Not Started | 0% | Deployment