## Worksheet
Task | Start Date | End Date | Status | Responsible | Progress (%)
Project Initiation | 01/03/2024 | 05/03/2024 | Completed | John Doe | 100%
Requirement Gathering | 06/03/2024 | 20/03/2024 | In Progress | Jane Smith | 75%
Design Phase | 21/03/2024 | 30/04/2024 | Planned | Alex Chen | 0%
Development | 01/05/2024 | 30/06/2024 | Not Started | Mike Brown | 0%
Testing & QA | 01/07/2024 | 30/08/2024 | Not Started | Sarah Lee | 0%
Deployment | 01/09/2024 | 30/09/2024 | Not Started | David Wilson | 0%
Review & Closeout | 01/10/2024 | 31/10/2024 | Planned | Team Lead | 0%