## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Project Initiation | 2024-01-01 | 2024-01-15 | John Doe | Completed | 100%
Requirements Gathering | 2024-01-16 | 2024-02-15 | Jane Smith | In Progress | 75%
Design Phase | 2024-02-16 | 2024-03-31 | Alex Brown | Not Started | 0%
Development | 2024-04-01 | 2024-05-31 | Sam Wilson | Not Started | 0%
Testing & QA | 2024-06-01 | 2024-07-15 | Lisa Chen | Not Started | 0%
Deployment | 2024-07-16 | 2024-07-31 | Mike Taylor | Not Started | 0%