## Project Timeline - Summary View
Task Name | Start Date | End Date | Status | Progress (%) | Responsible Person | Priority Level th>
Project Initiation Phase | 2024-01-15 | 2024-01-31 | Completed | 100% | Jane Smith | High
Requirements Gathering | 2024-02-01 | 2024-02-15 | In Progress | 75% | John Doe | High
Design Phase (UI/UX) | 2024-02-16 | 2024-03-10 | Pending | 0% | Lisa Chen | Middle
Development Phase (Backend) | 2024-03-11 | 2024-05-30 | Not Started | 0% | Marcus Lee | High
Testing & QA Phase | 2024-06-01 | 2024-07-15 | Not Started | 0% | Sophie Garcia | Middle
Deployment & Go-Live | 2024-07-16 | 2024-07-31 | Not Started | 0% | Raj Patel | High