## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Project Initiation | Alice Johnson | 2024-01-15 | 2024-01-30 | Completed | 100% | - | All stakeholders on board.
Requirements Gathering | Bob Smith | 2024-02-01 | 2024-02-15 | In Progress | 65% | Project Initiation complete | Client feedback pending.
Design Phase | Carol Lee | 2024-02-16 | 2024-03-15 | Not Started | 0% | Requirements finalized | Waiting for approval of scope.
Development Phase | David Wong | 2024-03-16 | 2024-05-31 | Not Started | 0% | Design phase completed | Team ready upon design approval.
Testing & QA | Eva Martinez | 2024-06-01 | 2024-06-30 | Not Started | 0% | Development phase complete | Scheduled after dev completion.
Deployment & Go-Live | Frank Brown | 2024-07-01 | 2024-07-15 | Not Started | 0% | Testing completed | Rollout to production environment.