## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Progress (%) | Notes
Project Initiation | 2024-01-01 | 2024-01-15 | Project Manager | Completed | 100% | All stakeholders aligned; scope finalized.
Requirements Gathering | 2024-01-16 | 2024-02-15 | Business Analysts | In Progress | 75% | Final review scheduled for 02/18.
Design Phase | 2024-02-16 | 2024-03-31 | UI/UX Team | Pending Start | 0% | Design mockups to be approved by 03/15.
Development Phase | 2024-04-01 | 2024-06-30 | Software Engineers | Not Started | 0% | Scheduled to begin after design approval.
Testing & QA | 2024-07-01 | 2024-08-31 | QA Team | Not Started | 0% | Will begin post-development completion.
Deployment & Launch | 2024-09-01 | 2024-09-30 | DevOps Team | Not Started | Final deployment to production environment.
Template Version 1.0 – Performance Tracking Project Timeline