## Worksheet
Task | Start Date | End Date | Status | Responsible Person | Progress (%) | Priority
Project Kickoff Meeting | 2024-01-15 | 2024-01-15 | Completed | Jane Smith | 100% | High
Requirements Gathering | 2024-01-16 | 2024-01-31 | In Progress | John Doe | 75% | High
Design Phase | 2024-02-01 | 2024-02-15 | Not Started | Lisa Chen | 0% | Medium
Development Phase | 2024-03-01 | 2024-04-30 | Not Started | Mark Taylor | 0% | High
Testing & QA | 2024-05-01 | 2024-05-31 | Not Started | Sarah Kim | 0% | High
Deployment & Launch | 2024-06-01 | 2024-06-15 | Not Started | David Lee | 0% | High