## Worksheet
Project Name | Team Member | Start Date | End Date | Status | Progress (%) | Key Milestones | Performance Rating (1-5) | Issues/Challenges | Next Actions
Web Platform Redesign | Sarah Johnson | 2024-03-15 | 2024-06-30 | On Track | 85% | UI Finalized, Backend API Completed | 4 | Minor delay in design approvals | Finalize testing schedule by May 10
Mobile App Launch | David Chen | 2024-04-01 | 2024-07-15 | Delayed | 50% | Alpha Testing Started, User Feedback Collected | 3 | High user feedback latency, limited QA resources | Hire temporary QA testers by May 15
Data Migration Initiative | Lisa Wong | 2024-03-20 | 2024-08-31 | On Track | 75% | Data validation completed, backup verified | 5 | None reported | Complete final migration and documentation by August 30