## Worksheet
Project Name | Start Date | End Date | Status | Progress (%) | Responsible Person | Budget (USD) | Actual Spend (USD) | Next Milestone | Performance Notes
Website Redesign | 2024-03-15 | 2024-06-30 | On Track | 75% | Sarah Johnson | 50,000.00 | 38,500.00 | Launch MVP in May | UI finalized; frontend development underway.
Mobile App Development | 2024-04-01 | 2024-10-31 | In Progress | 45% | Michael Chen | 120,000.00 | 62,300.00 | Beta testing in July | Backend integration completed; API testing pending.
Customer Onboarding Platform | 2024-05-01 | 2024-11-30 | Planned | 5% | Lisa Torres | 80,000.00 | 12,500.00 | Requirements finalization in June | Feasibility study completed; team assembling.