## Worksheet
Project Name | Start Date | End Date | Current Status | Progress (%) | Responsible Team | Budget (USD) | Actual vs. Planned | Key Milestones | Next Review Date
Product Launch Q4 | 2023-10-01 | 2023-12-31 | On Track | 85% | Product & Marketing | $500,000 | On Target | UI Finalized, Beta Launch (Nov 15) | 2023-11-15
Customer Onboarding System | 2023-09-05 | 2024-03-31 | In Progress | 45% | IT & Support | $320,000 | Below Plan | Phase 1 Complete, Phase 2 Pending | 2023-11-20
Sales Process Optimization | 2023-08-10 | 2024-01-31 | On Hold | 20% | Sales & Operations | $180,000 | On Track (adjusted) | Needs Stakeholder Approval | 2023-12-10