## Worksheet
Project Name | Client | Start Date | End Date | Status | Progress (%) | Budget (USD) | Actual Spend (USD) | Last Update
Website Redesign | ABC Corporation | 2024-03-15 | 2024-06-30 | On Track | 85% | 50,000 | 42,500 | 2024-05-12
Mobile App Development | XYZ Tech Inc. | 2024-04-01 | 2024-08-31 | In Progress | 60% | 75,000 | 48,000 | 2024-05-28
Marketing Campaign | Global Retail Group | 2024-05-05 | 2024-07-31 | Completed | 100% | 35,000 | 34,250 | 2024-07-15
E-commerce Platform Upgrade | OnlineMart Solutions | 2024-06-01 | 2024-10-31 | Planning Phase | 5% | 90,000 | 2,850 | 2024-06-18