## Worksheet
Project Name | Team | Start Date | End Date | Current Status | Progress (%) | Key Milestones | Owner | Risk Level | Next Review Date
Website Redesign | Design & Development Team | 2024-01-15 | 2024-06-30 | On Track | 75% | UI Design Approved, Backend Setup Complete | Sarah Johnson | Low | 2024-05-15
Mobile App Launch | Mobile Development Team | 2024-02-01 | 2024-08-31 | Delayed | 45% | Alpha Testing Completed, Beta Phase Pending | David Kim | Medium | 2024-06-10
Customer Analytics Platform | Data Science Team | 2024-03-10 | 2024-12-31 | On Track | 60% | Data Pipeline Built, Initial Models Trained | Lisa Chen | Low | 2024-09-15