## Worksheet
Project Name | Project ID | Start Date | End Date | Status | Assigned To | Progress (%) | Budget (USD) | Actual Spend (USD) | Key Milestones | Performance Score
Website Redesign | PRJ-2024-001 | 2024-03-01 | 2024-06-30 | On Track | Sarah Johnson | 85% | 150,000 | 120,500 | Launch v2.1 ¦ User Testing Complete | 8.7/10
Mobile App Development | PRJ-2024-002 | 2024-04-15 | 2025-01-31 | In Progress | Mark Reynolds | 45% | 200,000 | 85,200 | Beta Release (Q3) ¦ API Integration Done | 6.3/10
Customer CRM Upgrade | PRJ-2024-003 | 2024-05-10 | 2024-11-30 | On Track | Lisa Chen | 92% | 75,000 | 68,900 | System Integration ¦ Training Sessions | 9.4/10
Marketing Campaign 2024 | PRJ-2024-004 | 2024-06-01 | 2024-12-31 | Delayed | James Wilson | 30% | 50,000 | 28,750 | Launch Delayed to Q1 2025 ¦ Budget Reallocation | 4.1/10