## Worksheet
Project Name | Project Manager | Start Date | End Date | Current Phase | Budget (USD) | Actual Spend (USD) | Progress (%) | Status | Key Milestones | Risk Level | Owner Responsibility
Product Launch Q4 | Emma Watson | 2023-10-01 | 2023-12-31 | Development & Testing | 500,000.00 | 345,678.50 | 69% | In Progress | UI/UX Finalization, Beta Release, Market Rollout | Moderate | Product & Design Teams
CRM System Upgrade | James Reed | <2023-09-152024-03-31 | System Design & Planning | 250,000.00 | 89,456.25 | 36% | Pending Approval | Requirement Gathering, Vendor Selection, Architecture Review | Low | IT & Operations Leadership
Customer Support Platform Expansion | Sarah Kim | 2023-11-05 | 2024-06-30 | Implementation Phase | 420,000.00 | 198,765.34 | 47% | In Progress | API Integration, Training Module Setup, User Onboarding | Moderate | Support & HR Teams
Data Analytics Dashboard Revamp | David Liu | 2023-10-10 | 2024-05-31 | Design & Development | 380,000.00 | 295,432.17 | 77% | On Track | Dashboards Redesign, Real-Time Data Feeds, Security Audit | Low | Data Science & Engineering Team