## Worksheet
Project Name | Project Manager | Start Date | End Date | Current Status | Progress (%) | Budget (USD) | Actual Spend (USD) | Risk Level | Next Milestone
Website Redesign | Sarah Johnson | 2024-01-15 | 2024-04-30 | On Track | 75% | 50,000 | 37,500 | Low | Launch by April 25
Mobile App Development | Michael Chen | 2024-02-01 | 2024-06-30 | On Track | 55% | 120,000 | 65,000 | Medium | Beta Release – March 31
Customer Loyalty Program | Lisa Thompson | 2024-03-01 | 2024-09-30 | Delayed | 30% | 80,000 | 25,000 | High | Revised Timeline – May 15