## Worksheet
Project Name | Start Date | End Date | Current Status | Progress (%) | Assigned To | Next Milestone | Notes
Website Redesign | 2024-01-15 | 2024-06-30 | In Progress | 65% | Sarah Johnson | Launch UI Mockups (June 1) | Client feedback on wireframes pending.
Mobile App Development | 2024-03-01 | 2025-03-31 | Pending Approval | 20% | Mark Davis | Technical Requirements Finalized (April 15) | Waiting for stakeholder sign-off on scope.
Customer Portal Upgrade | 2024-02-10 | 2024-11-30 | On Track | 85% | Lisa Chen | User Testing Phase (October 15) | No major blockers identified.
Marketing Campaign Launch | 2024-04-05 | 2024-05-31 | Completed | 100% | Jamal Reed | Campaign Review (May 31) | Results show 35% increase in engagement.