## Worksheet
Project Name | Project Code | Start Date | End Date | Status | Assigned To | Budget (USD) | Actual Spend (USD) | Progress (%) | Key Milestones | Risk Level | Next Review Date
Customer Portal Redesign | PRJ-2024-001 | 2024-03-15 | 2024-06-30 | On Track | Alex Morgan | 150,000 | 125,400 | 83% | UI Finalization (Apr 1), Launch (Jun 30) | Low | 2024-05-15
Supply Chain Optimization | PRJ-2024-002 | 2024-04-01 | 2024-09-30 | On Hold | Sara Lee | 200,000 | 78,250 | 39% | Vendor Audit (Apr 15), Process Update (Aug 1) | Medium | 2024-07-01
Cloud Migration Initiative | PRJ-2024-003 | 2024-05-10 | 2024-11-30 | In Progress | Jordan Patel | 350,000 | 210,500 | 60% | Data Backup (May 25), Phase 2 Launch (Oct 1) | High | 2024-08-10
Marketing Campaign 2024 | PRJ-2024-004 | 2024-06-15 | 2024-12-31 | Planned | Mia Chen | 80,000 | 0 | 0% | Strategy Finalized (Jun 30), Launch (Aug 1) | Low | 2024-07-15