## Worksheet
Project Name | Start Date | End Date | Status | Progress (%) | Owner | Budget (USD) | Actual Spend (USD) | Next Milestone
Home Renovation | 2023-09-01 | 2024-03-31 | On Track | 75% | Sarah Johnson | 25,000 | 18,500 | Install Kitchen Cabinets (Mar 15)
Garden Upgrade | 2023-10-10 | 2024-01-30 | Completed | 100% | Mike Chen | 5,000 | 4,850 | Final Inspection (Jan 28)
Home Office Setup | 2023-11-05 | 2024-02-28 | In Progress | 40% | Emily Davis | 8,000 | 5,200 | Purchase Furniture (Dec 10)
Outdoor Lighting | 2023-12-01 | 2024-01-31 | On Hold | 0% | David Lee | 2,000 | 0 | Awaiting Permit Approval