## Worksheet
Project Name | Project Manager | Start Date | End Date | Current Status | Progress (%) | Budget (USD) | Actual Spend (USD) | Key Milestones | Risk Level | Next Review Date
Digital Transformation Initiative | Jane Doe | 01/03/2024 | 30/06/2024 | On Track | 75% | $500,000 | $375,000 | Phase I Complete ¦ Phase II In Progress | Medium | 05/07/2024
Customer Experience Platform | Mike Smith | 05/04/2024 | 31/08/2024 | On Track | 60% | $400,000 | $240,000 | UI/UX Design Complete ¦ Development Phase | Low | 10/07/2024
Supply Chain Optimization | Sarah Chen | 15/05/2024 | 30/09/2024 | Delayed | 40% | $750,000 | $320,000 | Vendor Onboarding ¦ Data Integration Phase | High | 05/08/2024