## Worksheet
Project Name | Start Date | End Date | Current Status | Progress % | Budget (USD) | Actual Spend (USD) | Owner | Last Updated | Notes
Customer Portal Redesign | 2023-04-01 | 2023-07-30 | On Track | 85% | 150,000 | 125,400 | Sarah Johnson | 2023-11-15 | UI/UX finalized; backend integration in progress.
Marketing Campaign Launch | 2023-06-10 | 2023-10-15 | Delayed | 45% | 75,000 | 38,200 | David Lee | 2023-11-14 | Ad platform issues; revised timeline approved.
Mobile App Development | 2023-03-05 | 2024-01-31 | On Track | 65% | 400,000 | 295,300 | Emma Chen | 2023-11-16 | Beta testing scheduled for Q1 2024.
Data Migration Project | 2023-10-15 | 2024-03-31 | At Risk | 25% | 180,000 | 67,800 | James Reed | 2023-11-13 | System compatibility issues identified.