## Worksheet
Project Name | Team Lead | Start Date | End Date | Current Status | Progress (%) | Key Milestones | Budget (USD) | Actual vs. Planned Spend | Performance Rating
Product Launch Q4 | Sarah Johnson | 2023-10-01 | 2023-12-31 | On Track | 85% | UI Design Finalized, Beta Testing Started | $150,000 | Within Budget | 4.5/5
Customer Portal Upgrade | Michael Chen | 2023-11-05 | 2024-01-30 | On Track | 70% | User Research Complete, MVP Built | $120,000 | Slightly Over Budget | 4.0/5
Marketing Campaign 2024 | Lisa Park | 2023-11-15 | 2024-03-31 | Delayed (Pending Approval) | 30% | Budget Approved, Strategy Finalized | $200,000 | On Track (Spend Adjusted) | 3.5/5
Internal Process Optimization | David Rodriguez | 2023-10-10 | 2024-02-28 | In Progress | 55% | Pilot Phase Running, Feedback Collected | $80,000 | Within Budget | 4.2/5