## Worksheet
Project Name | Start Date | End Date | Status | Progress (%) | Owner | Budget (USD) | Actual Spend (USD) | Risk Level | Next Milestone
Website Redesign | 2024-03-15 | 2024-06-30 | On Track | 75% | Sarah Chen | 50,000 | 38,500 | Medium | Launch MVP (May 15)
Mobile App Development | 2024-04-01 | 2024-09-30 | In Progress | 50% | James Lee | 120,000 | 65,200 | High | Beta Release (July 31)
Customer Portal Launch | 2024-05-01 | 2024-08-31 | Planned | 10% | Maria Lopez | 40,000 | 2,800 | Low | Design Finalized (June 15)
Marketing Campaign Rollout | 2024-06-01 | 2024-10-31 | Not Started | 0% | David Kim | 25,000 | 0 | Medium | First Phase Launch (July 1)