## Worksheet
Project Name | Project Manager | Start Date | End Date | Current Status | Progress (%) | Budget (USD) | Actual Spend (USD) | Next Milestone | Risk Level
Website Redesign | Alex Thompson | 2024-03-01 | 2024-06-30 | On Track | 85% | $50,000 | $42,500 | UI/UX Final Review (June 15) | Low
Mobile App Development | Jordan Lee | 2024-04-05 | 2024-09-30 | On Track | 60% | $100,000 | $65,000 | Beta Launch (July 20) | Medium
Customer Onboarding Platform | Megan Carter | 2024-05-10 | 2024-11-30 | Delayed | 35% | $75,000 | $30,000 | Phase II Development (Aug 1) | High
Marketing Automation System | Ryan Patel | 2024-06-01 | 2024-12-31 | On Track | 70% | $90,000 | $63,000 | Integration with CRM (Sept 30) | Low