## Worksheet
Project Name | Quarter | Objective | Key Performance Indicator (KPI) | Actual Performance | Target Goal | Status | Owner | Notes
Website Redesign | Q1 2024 | Improve user engagement through modern UI/UX. | Page load time < 2s | 1.8s | 2.0s | On Track | Jane Smith | User feedback collected; A/B testing underway.
Mobile App Launch | Q1 2024 | Achieve 50K downloads in first month. | Monthly downloads | 35K | 50K | On Track (Slowing) | John Doe | Marketing campaign delayed due to budget approval.
Customer Onboarding Flow | Q2 2024 | Reduce onboarding time by 30%. | Time to first task completion | 18 mins | 25 mins | On Track | Lisa Chen | Beta testing completed with positive feedback.
CRM Integration | Q3 2024 | Integrate sales and support systems. | System uptime > 99.5% | 98.7% | 99.5% | Below Target | Mark Wilson | Server migration issues during rollout.