## Worksheet
Project Name | Start Date | End Date | Current Status | Progress (%) | Owner | Budget (USD) | Actual Spend (USD) | Risk Level | Next Milestone
Website Redesign | 2024-03-15 | 2024-06-30 | On Track | 75% | Sarah Johnson | $50,000 | $37,500 | Low | UI Finalization (May 15)
Mobile App Development | 2024-04-01 | 2024-09-30 | On Track | 55% | Mike Chen | $120,000 | $66,000 | Medium | Backend Launch (July 20)
Customer Onboarding System | 2024-05-10 | 2024-11-30 | Delayed | 30% | Linda Park | $80,000 | $24,000 | High | Phase 1 Review (Aug 15)
Marketing Campaign Rollout | 2024-06-01 | 2024-12-31 | On Track | 85% | David Ross | $40,000 | $34,000 | Low | Final Analytics (Dec 25)