## Worksheet
Project Name | Start Date | End Date | Status | Assigned To | Progress % | Key Milestone | Next Action
Website Redesign | 2024-03-15 | 2024-06-30 | On Track | Jane Doe | 75% | Mobile UX Review | Finalize wireframes by May 10
Marketing Campaign | 2024-04-01 | 2024-05-31 | On Track | John Smith | 60% | Social Media Launch | Submit analytics report by May 15
App Development | 2024-03-20 | 2024-11-30 | In Progress | Alex Brown | 40% | Beta Testing Phase | Conduct user testing in April
Customer Onboarding System | 2024-05-01 | 2024-08-31 | Planned | Lisa Chen | 0% | Requirement Gathering | Schedule kickoff meeting in June