## Worksheet
Project Name | Team Member | Start Date | End Date | Current Status | Progress % | Key Milestones | Issues/Challenges | Next Action Item | Owner
Website Redesign | Alex Johnson | 2024-03-01 | 2024-05-31 | On Track | 85% | Launch v2.0, UX Audit Complete | Minor responsiveness issues on mobile | Finalize design mockups by April 15 | Samantha Lee
Mobile App Development | Jordan Patel | 2024-02-15 | 2024-07-30 | Delayed | 45% | Beta Testing Phase, API Integration | Backend delay in third-party services | Resolve API dependency by April 10 | Jordan Patel
Marketing Campaign Launch | Taylor Reed | 2024-04-01 | 2024-06-30 | On Track | 90% | Social media rollout, email sequence sent | None reported | Finalize analytics dashboard by May 15 | Taylor Reed