## Worksheet
Project Name | Team Member | Start Date | End Date | Current Status | Progress (%) | Key Deliverables | Next Milestone | Risk Level | Action Required
Website Redesign | Sarah Johnson | 2024-01-15 | 2024-03-30 | On Track | 85% | UI/UX Design, Responsive Layout | Launch Beta Version | Low | Review user feedback weekly
Mobile App Development | Michael Chen | 2024-02-01 | 2024-05-15 | In Progress | 60% | Authentication Module, API Integration | User Testing Phase | Medium | Fix login bugs by Feb 28
Marketing Campaign Launch | Lisa Wang | 2024-03-01 | 2024-04-15 | Planned | 30% | Social Media Ads, Email Sequences | Approval of Budget | Low | Finalize ad creatives by March 15
Product Roadmap Update | David Lee | 2024-01-30 | 2024-06-30 | Pending Initiation | 15% | Feature Prioritization, Stakeholder Alignment | Kickoff Meeting | High | Schedule meeting with stakeholders by Feb 20