## Worksheet
Week | Project Name | Start Date | End Date | Status | Progress (%) | Key Milestones | Owner | Notes
Week 1 | Website Redesign | 2024-04-01 | 2024-04-30 | In Progress | 35% | UI mockups approved, design finalized | John Doe | Client feedback scheduled for Week 2.
Week 2 | Mobile App Development | 2024-04-08 | 2024-05-15 | On Track | 60% | Backend API completed, frontend in progress | Jane Smith | Testing phase scheduled for Week 3.
Week 3 | Marketing Campaign Launch | 2024-04-15 | 2024-05-31 | Pending Start | 0% | Final budget approved, content in review | Mike Johnson | Waiting on final approval from sales team.
Week 4 | Customer Support System Upgrade | 2024-04-22 | 2024-06-15 | Not Started | 0% | Needs requirements gathering | Sarah Lee | Stakeholder meetings planned for Week 5.