## Worksheet
Date | Team Member | Task | Status | Target Completion Time | Actual Completion Time | Performance Score (1-5) | Comments / Notes
2024-04-01 | Alex Morgan | Product Requirement Analysis | Completed | 2024-04-03 | 2024-04-03 | 5 | Well structured, delivered on time.
2024-04-02 | Jordan Lee | User Interviews (Phase 1) | In Progress | 2024-04-05 | - | 4 | Interviews scheduled, awaiting feedback.
2024-04-03 | Samira Patel | UI/UX Wireframe Drafting | Pending | 2024-04-07 | - | 3 | Needs refinement based on user feedback.
2024-04-04 | David Chen | Backend API Development | Not Started | 2024-04-10 | - | 1 | Waiting on database schema approval.
2024-04-05 | Lena Torres | Performance Testing (Beta) | Completed | 2024-04-05 | 2024-04-05 | 5 | No critical bugs found. Good stability.