## Worksheet
Task | Assigned To | Due Date | Priority | Status | Progress (%) | Notes
Research market trends | Sarah Johnson | 2024-04-15 | High | In Progress | 65% | Initial data collected from 3 industry reports.
Finalize product specifications | Michael Chen | 2024-04-25 | High | Not Started | 0% | Waiting for design team feedback.
Prepare marketing campaign | Lisa Park | 2024-05-10 | Medium | On Hold | 30% | Budget approval pending.
Conduct customer feedback survey | David Ruiz | 2024-04-30 | Medium | Completed | 100% | Results analyzed; key insights documented.
Train sales team on new product | Emma Wong | 2024-05-05 | Low | Scheduled | 0% | Training materials being prepared.