## Worksheet
Task / Activity | Responsible Party | Start Date | End Date | Status | Progress (%) | Remarks
Initial Supply Assessment | Planning Team | 2024-03-01 | 2024-03-15 | Completed | 100% | Full inventory review conducted.
Procurement of Raw Materials | Procurement Department | 2024-03-16 | 2024-04-10 | In Progress | 75% | Delays in supplier response.
Equipment Inspection & Calibration | Maintenance Unit | 2024-04-11 | 2024-04-25 | Pending | 0% | Waiting for scheduling approval.
Delivery & Onsite Setup | Logistics Team | 2024-04-26 | 2024-05-10 | Not Started | 0% | No delivery schedule confirmed.