## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Progress (%) | Start Date | Completion Date | Notes
T001 | Design Website UI | John Doe | 2024-04-15 | In Progress | High | 65% | 2024-03-20 | - | Final mockups to be approved by design team.
T002 | Develop Backend API | Jane Smith | 2024-04-25 | Pending | High | 0% | 2024-03-25 | - | Waiting for database schema confirmation.
T003 | Conduct User Testing | Alice Johnson | 2024-05-10 | Planned | Medium | 0% | 2024-04-05 | - | Recruit 15 participants from beta group.
T004 | Prepare Project Report | Robert Lee | 2024-05-30 | Completed | Low | 100% | 2024-05-15 | 2024-05-28 | Submitted to stakeholders on May 28.
T005 | Organize Team Meeting | Sarah Kim | 2024-04-18 | Completed | Low | 100% | 2024-04-15 | 2024-04-17 | Meeting notes shared in team drive.