## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Progress (%) | Start Date | Estimated Hours | Actual Hours | Remarks
T001 | Finalize Q4 Marketing Strategy | Anna Smith | 2024-05-30 | High | In Progress | 75% | 2024-04-15 | 8 | 6 | Needs client feedback on campaign ideas.
T002 | Develop New User Onboarding Flow | James Lee | 2024-06-15 | Medium | Not Started | 0% | 2024-05-01 | 12 | 0 | Design mockups pending approval.
T003 | Conduct Quarterly Performance Review | Sophia Chen | 2024-06-25 | High | Completed | 100% | 2024-05-20 | 6 | 6 | All team members reviewed and feedback collected.
T004 | Upgrade Server Infrastructure | Michael Brown | 2024-07-10 | Critical | In Planning | 20% | 2024-06-01 | 15 | 0 | Vendor evaluation underway.