## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Progress (%) | Notes
TP-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | Completed | High | 100% | All stakeholders aligned on goals.
TP-002 | <:// 2.4Design Phase Finalization | Maria Lopez | 2024-04-05 | 2024-04-15 | In Progress | Medium | 65% | UI mockups approved by product team.
TP-003 | Backend Development Setup | David Chen | 2024-04-10 | 2024-05-10 | Pending Start | High | 0% | Waiting on API documentation.
TP-004 | User Testing & Feedback Loop | Sophia Kim | 2024-05-15 | 2024-06-15 | Planned | Medium | 0% | Scheduled for beta release phase.