## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Progress (%) | Remarks
T-001 | Project Kickoff Meeting | Jane Doe | 2024-04-05 | Completed | High | 100% | All stakeholders confirmed attendance.
T-002 | Requirement Gathering | John Smith | 2024-04-15 | In Progress | Medium | 65% | Final review scheduled for April 10.
T-003 | UI/UX Design Draft | Lisa Chen | 2024-04-20 | Pending | High | 0% | Awaiting client feedback.
T-004 | Backend Development | Mike Johnson | 2024-05-03 | Planned | Medium | 0% | Development team on standby.
T-005 | Performance Testing | Sarah Lee | 2024-05-15 | Not Started | High | 0% | Schedule pending final design approval.