## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Progress (%) | Notes
T001 | Project Kickoff Meeting | Jane Smith | 2024-04-15 | Completed | Medium | 100% | All stakeholders aligned on project scope.
T002 | Design Phase Final Review | Mike Johnson | 2024-04-25 | In Progress | High | 75% | Design mockups submitted; awaiting feedback.
T003 | Development Environment Setup | Sarah Lee | 2024-05-10 | Not Started | Medium | 0% | Waiting for server access approval.
T004 | Testing Strategy Document | David Kim | 2024-05-20 | Completed | Low | 100% | All test cases defined and reviewed.