## Worksheet
Task ID | Task Name | Owner | Start Date | Due Date | Status | Progress (%) | Priority | Estimated Hours | Actual Hours | Performance Rating
T-001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | 100% | Low | 2.5 | 2.5 | Excellent
T-002 | Market Research Analysis | Emily Davis | 2024-03-20 | 2024-04-10 | In Progress | 65% | Medium | 8 | 5.2 | Good
T-003 | UI/UX Design Finalization | Michael Chen | 2024-04-01 | 2024-05-15 | Pending | 0% | High | 12 | 0 | Needs Action
T-004 | Development Sprint Planning | Sarah Lee | 2024-04-10 | 2024-05-31 | Completed | 100% | Medium | 15 | 14.8 | Excellent