## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Progress (%) | Comments
T-001 | Develop User Authentication Module | John Doe | 2024-03-15 | High | In Progress | 65% | Integration with third-party login providers still pending.
T-002 | Design Mobile UI/UX Prototype | Sarah Kim | 2024-03-10 | Medium | Not Started | 0% | Needs alignment with product team.
T-003 | Optimize Database Query Performance | Mike Chen | 2024-03-20 | High | Completed | 100% | Performance improved by 35%. Report attached.
T-004 | Set Up CI/CD Pipeline | Emily Reed | 2024-03-18 | Medium | In Progress | 40% | Waiting on infrastructure team to approve resources.
T-005 | Conduct Security Audit | David Wu | 2024-03-25 | High | Planned | 0% | External vendor to be engaged next week.